MSc Masters Project

PROJECT PROCESS DOCUMENTATION TEMPLATE

Student(s): JAMES EBUKELEY FORSON 	Supervisor: MAZHAR MALIK

Meeting Number: 1 Date/Time: 5th February 2026 / 12:00 pm – 1:00 pm

Agenda for meeting: MSc Project – Initial Supervision meeting.

Discussion of agenda items:

- The supervisor informed the student about the total number of students assigned to him for supervision this academic period.

- The formality and structure expected in the MSc Project work specification were discussed in detail.

- Clear guidance was provided on preparing and submitting the research specification to the supervisor for review and approval.

Summary of agreed action plan:

- The student agreed to prepare a detailed research specification (including research topic, objectives, questions, and proposed methodology) and submit it to the supervisor for review and feedback by 20th February 2026.

- Any questions regarding the project expectations to be clarified via email before submission.

Notes:

- This was the initial supervision meeting.

- The student demonstrated good understanding of the project requirements.

- Positive start to the supervision process.

Meeting Number: 2 Date/Time: 5th March 2026 / 12:00 pm – 1:00 pm

Agenda for meeting: Reviewing progress and what to do in March 2026.

Discussion of agenda items:

- The supervisor confirmed that the research specification submitted by the student had been reviewed and officially signed off.

- Discussion focused on commencing the core research work, specifically the drafting of Chapters 1 to 3 (Introduction, Literature Review, and Research Methodology).

- The student was advised on the expected quality, structure, and timelines for submitting these chapters for review.

Summary of agreed action plan:

- The student to proceed with writing Chapters 1-3 and submit the drafts to the supervisor for review by the end of March 2026.

- Schedule the next supervision meeting in early April to review progress on the initial chapters.

Notes:

- Good progress noted with the approval of the research specification.

- Emphasis placed on maintaining academic rigor in the literature review.

Meeting Number: 3 Date/Time: 2nd April 2026 / 2:00 pm – 3:00 pm

Agenda for meeting: Reviewing the guidelines for the final research report submission and viva.

Discussion of agenda items:

- The supervisor reviewed the submitted research report Chapters 1-3 and provided detailed feedback.

- Comprehensive discussion on the guidelines for the final research report submission, including formatting, referencing style, and completeness requirements.

- Guidelines for the viva voce examination were explained, including expectations for the presentation and defense of the research work.

- Advice was given on the student’s preparation towards the viva (e.g., practicing presentation, anticipating questions).

Summary of agreed action plan:

- Students agreed to submit their research reports to the Supervisor for review before 10th of April 2026.

- Students agreed to accept the date assigned to them for their viva.

Notes:

- Chapters 1-3 were generally well-received with some areas identified for improvement.

- Student advised to incorporate feedback promptly.

- Preparation for viva is critical for successful completion of the MSc project.